## Plan
Section | What to write | Your plan | Example
Document control | Who owns the plan, which version this is, and who must approve it. (Plan title; Plan ID and version; Date; Author; Approvers; Revision history) |  | Test plan for Acme Shop 2.0 launch. ID TP-ACME-2.0, version 1.0, 14 October 2026. Author: QA lead. Approvers: product owner, engineering lead.
Introduction and context | What is being tested and why, and what the testing is based on. (Product and release; Purpose of this test plan; Test basis (requirements, designs, user stories, contracts)) |  | This plan covers testing of the Acme Shop web store and iOS app before the 2.0 launch on 1 December 2026. Test basis: product requirements v3, Figma designs, Jira epics ACME-100 to ACME-180.
Scope | What will be tested and, just as important, what will not, with a reason. (Features in scope; Features out of scope and why; Platforms in scope) |  | In scope: signup, login, password reset, search, cart, checkout, payments, order emails. Out of scope: warehouse integration (tested by the vendor), legacy admin reports (unchanged).
Test objectives | What the testing must prove or find. (Objectives) |  | Confirm core purchase flows work on the agreed devices; find critical and major defects before launch; confirm payments, taxes and emails are correct; confirm WCAG 2.2 AA on key flows.
Assumptions and constraints | What you are counting on and what limits the testing. (Assumptions; Constraints (time, budget, people, environments)) |  | Assumes a stable staging environment with production-like data from 3 November. Constraint: two testers for four weeks; no access to production payments before launch day.
Test approach | How you will test. Test levels, types, techniques, manual vs automated, and who tests. (Test levels (component, integration, system, acceptance); Test types (functional, regression, compatibility, accessibility, performance, security basics); Techniques; Manual vs automated split; Independence of testing) |  | System and acceptance testing by an independent QA team. Functional testing with the BugsQA test cases for login, signup, reset, search, cart, checkout and payments; exploratory sessions on new features; automated regression smoke suite on every build; accessibility checks against WCAG 2.2 AA.
Test environments, devices and accounts | Where testing happens and on what. (Environments and URLs; Devices and browsers; Test accounts and roles; Tools) |  | Staging at staging.acme.example. Devices: iPhone (iOS 27, Safari), Samsung Galaxy (Android 16, Chrome and Samsung Internet), Windows 11 Chrome and Edge, macOS Safari, iPad. Accounts: customer, new customer, admin. Tools: Jira, TestRail, BrowserStack.
Test data | The data you need and where it comes from. Never use real customer personal data without permission. (Test data needed; Source of data; Privacy rules) |  | Stripe test cards; 50 products incl. out-of-stock and multi-variant; addresses in 5 US states and 4 Canadian provinces; no real customer data on staging.
Entry criteria | What must be true before testing starts (Definition of Ready in agile teams). (Entry criteria) |  | Build deployed to staging; smoke tests pass; test accounts and data ready; requirements for the release signed off; known open issues listed.
Exit criteria | What must be true to call testing done (Definition of Done). Can include accepting risk if time runs out, as long as stakeholders agree. (Exit criteria) |  | All high priority test cases executed and passed; no open critical (S1) or major (S2) defects; minor defects reviewed and accepted by the product owner; regression suite green on the release candidate.
Suspension and resumption criteria | When to pause testing, and what is needed to resume. (Suspend when; Resume when) |  | Suspend if the build fails smoke tests or a blocker stops more than 30% of planned tests. Resume when a fixed build passes smoke tests.
Risk register | Product risks (what could go wrong for users) and project risks (what could stop testing), each with likelihood, impact and response. (Risk; Type (product or project); Likelihood (1 to 3); Impact (1 to 3); Score; Response) |  | Payment webhook fails and orders are not created (product; likelihood 2, impact 3, score 6; mitigate with dedicated payment tests and monitoring). Staging unavailable for a week (project; likelihood 1, impact 3; contingency: test on a preview environment).
Roles and responsibilities | Who does what. A simple RACI works well. (Role; Name; Responsibilities) |  | QA lead: plan, triage, report. Testers: execute, report bugs. Developers: fix, unit test. Product owner: priorities, acceptance, sign-off.
Defect management | How bugs are reported, rated and tracked. (Tool; Severity scale; Priority scale; Workflow; Triage meeting) |  | Jira. Severity S1 to S4 and priority P1 to P4 (see scales). Workflow: New, Open, In progress, Ready to retest, Closed or Reopened. Daily 15 minute triage during the test window.
Communication and reporting | How and how often the team hears about testing progress. (Status report cadence; Channels; Metrics) |  | Daily summary in Slack; weekly report with tests run, pass rate, open defects by severity; final test summary report before go or no-go.
Test deliverables | What testing will produce. (Deliverables) |  | This test plan, test cases, bug reports, daily status, test summary report, go or no-go recommendation.
Schedule and milestones | Key dates for testing. (Milestone; Date) |  | Test cases ready 31 Oct; testing 3 to 21 Nov; regression 24 to 26 Nov; go or no-go 27 Nov; launch 1 Dec.
Budget and effort (optional) | Estimated effort or cost. (Effort estimate; Budget) |  | Two testers for four weeks (about 320 hours) plus a device cloud subscription.
Approval and sign-off | Who agrees to the plan and, at the end, to release. (Name; Role; Signature or approval date) |  | Product owner, engineering lead, QA lead.
Glossary and references | Terms and documents the reader may need. (Terms; Referenced documents) |  | Severity, priority, regression, smoke test, UAT. References: requirements v3, design files, release notes.

## Risk register
Risk | Type (product or project) | Likelihood (1 to 3) | Impact (1 to 3) | Score | Response | Owner
Payment webhook fails and orders are not created | Product | 2 | 3 |  | Dedicated payment tests and monitoring | QA lead

## Schedule
Milestone | Start | End | Owner | Status
Test plan approved |  |  |  | Not started
Test cases and test data ready |  |  |  | Not started
Testing |  |  |  | Not started
Regression and retests |  |  |  | Not started
Go or no-go decision |  |  |  | Not started
Release |  |  |  | Not started